## Instructions
GIRLS' EDUCATION CHALLENGE - TRANSITION WINDOW (GEC-T) LOGICAL FRAMEWORK TEMPLATE A logical framework or logframe is required for all GEC projects. Applicants are asked to fully complete all sections of the logical framework - noting that further revision is possible during the inception stage. Please refer to the guidance associated with this logframe template for more detailed information on how to complete it. Please pay particular attention to the section on boys and gender disaggregation. IMPORTANT INFORMATION ON COMPLETING THE LOGFRAME • Each logframe must be saved as a separate file in Excel format (*.xls) • The font should be no smaller than Arial 9 when completed. • Information on Outcome 1 and Outcome 2 on learning and transition respectively will be complemented by a more in-depth Outcomes Spreadsheet to be submitted alongside the project Baseline. • Note that Outcomes 1 and 2 allow for data on boys to be reported where this is feasible and makes sense in the context of your intervention. Note however that as the core focus should still be on your target girls, there is no expectation to set targets for boys. • Similar disaggregation of reporting by gender is permissable at the Intermediate Outcome and Output levels where applicable, and only where it is relevant. • The logframe must include between 3 and 5 Intermediate Outcomes, including the compulsory attendance Intermediate Outcome. Please delete Intermediate Outcome rows not used. • Data for all Outcomes and Intermediate Outcomes should be collected by the project's external evaluator at evaluation points (Baseline and subsequent evaluation points). Outcome and Intermediate Outcome impacts and targets must clearly match the relevant indicator. • The logframe must not include any more than 6 Outputs. • Output indicators must be reported against annually and can come from project's own internal monitoring and data collection. Impact and targets must clearly match the relevant output indicator and will be assessed as part of the Annual Review of each project. There should be no more than 4 indicators per Output. • Projects are required to set Output weightings for each Output. The Output weightings should reflect the weight of contribution of each output to the Intermediate and Full Outcomes. The sum total of budget weightings must equal 100%. • The assumptions and risks column must be completed for all indicators in all sections. Logframes which do not conform to the above criteria will not be considered.

## Outcomes 1,2 - IOs
Project: | GATE-GEC | Lead Partner: | Plan International UK
Project number: | 5096 | Country: | Sierra Leone
OUTCOME 1 - Learning | Literacy Improvement |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020 | Assumptions
Improved learning outcomes in literacy and numeracy for marginalised girls supported by GEC (with sub-indicator for boys with disabilities where reported) | Average literacy test score, weighted by grade, as percentage points above control group | Primary girls (Disaggregate by disability, age, district, intervention type) |  | +5.1% |  | Beneficiaries and communities (including boys) are supportive of interventions and continue to be involved. Schools and their communities are receptive to field staff collecting data from both schools as well as study groups. Re-contacting original GEC Project Baseline verification girls possible (ensure clear ID s are kept, verification data up to date). Political will of government to work in partnership with INGOs is maintained.
|  | Secondary girls (Disaggregate by disability, age, district, intervention type) | 50.7% (girls, JSS) | Actual | Actual
Primary boys (Disaggregate by disability, age, district, intervention type)
|  | Secondary boys (Disaggregate by disability, age, district, intervention type) | 51.4% (boys, JSS) (This is an extremely small sample of approx. 20 boys and therefore comparability is not possible) | suggest to capture this differently at midline/endline as cwd (see rows below)
|  | Primary children with disabilities (disaggregate by gender, type of disability, district, age) |  | +2.4%
|  | Secondary children with disabilities (disaggregate by gender, type of disability, district, age) | 54.7% (small sample size of 34) | suggest to capture at midline | suggest to capture at endline
| Input (HR) |  | DFID (FTEs) | Consortium (FTEs) | Others (FTEs) | Source
| Inputs (£) |  | DFID (£) | Consortium (£) | Others (£) | External Evaluator. Learning assessments/tests (EGRA,SEGRA). Please note on intervention type, we will have to assess where this is possible following a review with the midline consultants. we will look to include additional questions to identify the intervention type that the treatment group are exposed to and make use of the project tracking tool/verification data will be required). Project monitoring: EE's Review of Project reverification data (includes literacy exam results)
| Numeracy improvement |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020
| Average mathematics test score, weighted by grade, as percentage points above control group | Primary girls (Disaggregate by disability, age, district, intervention type) |  | +3.6% |  | Beneficiaries and communities (including boys) are supportive of interventions and continue to be involved. Schools and their communities are receptive to field staff collecting data from both schools as well as study groups. Re-contacting original GEC Project Baseline verification girls possible (ensure clear ID s are kept, verification data up to date). Political will of government to work in partnership with INGOs is maintained.
|  | Secondary girls (Disaggregate by disability, age, district, intervention type) | 50.2% (girls, JSS) | Actual | Actual
Primary boys (Disaggregate by disability, age, district, intervention type)
|  | Secondary boys (Disaggregate by disability, age, district, intervention type) | 56.8% (boys, JSS) | suggest to capture this differently at midline/endline as cwd (see rows below)
|  | Primary children with disabilities (disaggregate by gender, type of disability, district, age) |  | +3.7%
|  | Secondary children with disabilities (disaggregate by gender, type of disability, district, age) | 53.1% (small sample size of 34) | suggest to capture at midline | suggest to capture at endline
| Input (HR) |  | DFID (FTEs) | Consortium (FTEs) | Others (FTEs) | Source
| Inputs (£) |  | DFID (£) | Consortium (£) | Others (£) | External Evaluator: Learning assessments/tests (EGMA,SEGMA). Please note on intervention type, we will have to assess where this is possible following a review with the midline consultants. we will look to include additional questions to identify the intervention type that the treatment group are exposed to and make use of the project tracking tool/verification data will be required). Project monitoring: EE's Review of Project reverification data (includes numeracy exam results)
RISK RATING Medium
OUTCOME 2 - Transition | Outcome Indicator |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020 | Assumptions
More marginalised girls transition through key stages of education, training or employment (with sub-indicator for boys where reported) | Transition Rate, weighted by grade, as percentage points above control group | Primary (disaggregate by gender, disability, district, intervention type) |  | +8% | +7% | Beneficiaries and communities (including boys) are supportive of interventions and continue to be involved. Schools and their communities are receptive to field staff collecting data from both schools as well as study groups. Re-contacting original GEC Project Baseline verification girls possible (ensure clear ID s are kept, verification data up to date). Political will of government to work in partnership with INGOs is maintained.
|  |  | 77.34% (girls) | Actual | Actual
|  | JSS (disaggregate by gender, disability, district, intervention type) |  | +8% | +8%
|  |  | 66.42% (boys) | Actual | Actual
| Input (HR) |  | DFID (FTEs) | Consortium (FTEs) | Others (FTEs) | Source
| Inputs (£) |  | DFID (£) | Consortium (£) | Others (£) | External Evaluator: Transition Rates using Enrolment, attendance and drop out data from household surveys., School Master results sheet. Please note on intervention type, we will have to assess where this is possible following a review with the midline consultants. we will look to include additional questions to identify the intervention type that the treatment group are exposed to and make use of the project tracking tool/verification data will be required). Project monitoring: EE's Review of Project reverification data (includes repetition, promotion rates and exam results)
RISK RATING High
OUTCOME 3 - Sustainability | SEE 'OUTCOME 3 SUSTAINABILITY' TAB
INTERMEDIATE OUTCOME 1 | IO Indicator 1 |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020 | Assumptions | Definitions/Index of questions
Improved attendance of the GEC cohort in schools throughout the life of the project | IO 1.1: Attendance of the GEC cohort in schools throughout the life of the project (school register) | JSS Schools (disaggregate by gender, disability, age, district, intervention type (where possible) |  | +1% | +1% | Communities are supportive of interventions and continue to be involved. Bursaries incentivise girls to enrol and stay in school and attend regularly. Schools are willing to enrol children with disabilities. | GEC cohort '- girls and children with disability that were a part of the GEC 1 project (2013-2016) At Baseline, attendance was measured based on school data (registers and HTs) - average attendance rate last year. There is a wide-spread issue in schools with generally poor accuracy of attendance data (due to lack of timeliness in completing them and lack of understanding of the role of attendance monitoring and follow up). At Midline, the GATE-GEC project team will have undertaken sensitisation activities and support with schools to improve the accuracy and timeliness. This may mean that attendance data is lower than reported at Baseline, however it should be a truer reflection of the reality and will help us to see more meaningful change over time.
|  |  | 90.99% (girls) | Actual | Actual
|  | PS schools (disaggregate by gender, disability, age, district, intervention type (where possible) | 79.84% (girls) | Actual | Actual
| IO 1.2: Improvement in attendance of the GEC cohort in schools throughout the life of the project (attendance spot checks) | JSS schools (disaggregate by gender, disability, age, district, intervention type (where possible) | Data not captured at baseline, but suggested/recommended by baseline consultants to capture at midline/endline |  |  |  | GEC cohort '- girls and children with disability that were a part of the GEC 1 project (2013-2016) Measurement to be agreed with midline consultants
|  |  |  | Actual | Actual
|  | PS schools (disaggregate by gender, disability, age, district, intervention type (where possible - use of project tracking tool/verification data will be required)) |  | Actual | Actual
RISK RATING Medium | External Evaluators: Baseline, Midline and Endline: Household survey with parents and children, School survey and Qual interviews: FGDs and KIIs with children, parents, teachers. Classroom observations. Girls School survey. Please note on 'intervention type', we will have to assess where this is possible following a review with the midline consultants. we will look to include additional questions to identify the intervention type that the treatment group are exposed to and make use of the project tracking tool/verification data will be required. Project monitoring: EE's Review of Study group attendance tracking ,attendance spot checks on school registers. Study group monitoring of beneficiaries, PVs (Teachers) and parents/caregivers. Study group observations. Bursary distribution and monitoring form.
INTERMEDIATE OUTCOME 2 | IO 2 Indicators |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020 | Assumptions | Definitions/Index of questions
Improved knowledge and demonstration of inclusive education and gender sensitive learning centred teaching in literacy and numeracy | IO 2.1: # of teachers (Head Teachers, PVs) with increased knowledge of inclusive education teaching methodologies in GATE GEC model schools. | PS Schools (disaggregate by HTs, PVs, gender) | Data not captured at baseline, but suggested/recommended by baseline consultants to capture at midline/endline |  |  | Teachers will be committed and will continue to engage with the project. The Ministry of Education continues to support the project. | Inclusive Education teaching methodologies - An Inclusive education system means that the whole education system considers the measures it must take to be able to provide an appropriate education with all children learning together. It takes into account the individual teaching and learning needs of all marginalised and vulnerable children and young people. Knowledge - The abilities/skills of teachers (including PVs) to facilitate inclusive teaching/ learning for benefit of all learners)
|  | JSS School (disaggregate by HTs, PVs, gender) |  | Actual | Actual
| IO 2.2: % of teaching staff (PVs and LAs/STs) demonstrating gender sensitive learning centred teaching practices | JSS Schools (disaggregate by PVs, LA/STs) |  | +7% | +7% | PVs, LAs and STs remain committed to interventions and incentivised to attend trainings. | Programme Volunteers are school teachers specially selected and recruited to run study groups in GATE GEC schools. Learning Assistants (and subsequently Student teachers) are Cohort 3 recruited under GATE-GEC. Baseline Index of percent of best practices in use according to classroom observations of PVs - % of questions answered 'yes). Targets equal to +0.5SD per year. For subsequent evaluation points an additional exploration of the effect of LAs in Study Group spaces.
|  |  | 68.4% (PVs only) | Actual | Actual
|  | Primary Schools (disaggregated by PVs, LA/STs) | 77.6% (PVs only) | Actual | Actual
| IO 2.3 (a): % of the GEC cohort reporting improved perceptions of learning in literacy | Girls (disaggregate by JSS/PS, district, age) |  | +5% | +5% | PVs, LAs and STs remain committed to interventions and incentivised to attend trainings | GEC cohort '- girls and children with disability that were a part of the GEC 1 project (2013-2016) During the baseline, index of two student questions: whether teachers ask more questions to boys or girls; and whether teachers ask harder questions to boys and girls. A different measure will be used to assess students' perceptions of learning at future evaluation points incorporating indicators such as - 'Ask questions freely', 'do homework', 'feel supported and positive in their study group', 'feel they have improved in their studies'. Targets equal to +0.25SD per year
|  |  | 53.2% (girls) and 50.3% (boys) (only captured at JSS) | Actual | Actual
|  | Children with Disabilities (disaggregate by gender, disability, JSS/PS, district, age) | To be added during midline inception phase | Actual | Actual
| IO 2.3 (b): % of the GEC cohort reporting improved perceptions of learning in numeracy | Girls (disaggregate by JSS/PS, district, age) |  | +5% | +5% | PVs, LAs and STs remain committed to interventions and incentivised to attend trainings | As above, however suggest midline consultants use a different set of index of questions/variables to measure this indicator also including the number of children that say they feel supported, and positive in their study group and 'have they improved in their studies'. The project feels this better reflects the indicator compared to the questions used by the baseline consultants.
|  |  | 53.2% (girls) and 50.3% (boys) (only captured at JSS) | Actual | Actual
|  | Children with Disabilities (disaggregate by gender, disability, JSS/PS, district, age) | Not captured at baseline as per the q's suggested | Actual | Actual
RISK RATING Medium | External Evaluators: Baseline, Midline and Endline: Classroom observations. Household survey with parents and children, KIIs and FGDs with teachers and beneficiaries. Classroom observations. Girls School survey. Learning test scores. Project monitoring: EE's Review of study group observations, FGDs and KIIs with children, parents, teachers (PVs), LAs and STs (that are involved in the study groups). Exam report cards and tracking these at relevant points post exams. Pre and post training assessments with observations of the trainings, Event completion forms. Inclusive pedagogical practice and school environment tool and academic result tool. Study group monitoring of PVs, beneficiaries and parents. CPD review tool. LAs and ST self assessments. End of unit Head Teacher/LA Adviser reported observations, LA post-unit assessments. Termly ST self reflections on classroom practices, Termly ST classroom observation reports by Study and Practice Mentor (with specific look at inclusive education). In-school experience attendance monitoring. Reverification data. HI inclusive education tools.
s
INTERMEDIATE OUTCOME 3 | IO 3 Indicators |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020 | Assumptions | Definitions/Index of questions
Improved sense of self-esteem, confidence and agency amongst marginalised girls and children with disabilities in relation to their education (including feeling safe and secure) | IO 3.1: % of girls and children with disabilities reporting positive self-esteem to participate and learn in school | Girls (disaggregate by JSS/PS, district, age) |  | +6% | +6% | Beneficiaries and communities (including boys) are supportive of interventions and continue to be involved. | This indicator explores both the level of confidence of beneficiaries to participate in their education and transition; as well as the extent to which beneficiaries feel they have agency to make choices around their transition. Analysis should explore each of these concepts, and progress against this indicator will be an aggregate measure. Please note the baseline Index Score of Self-Esteem questions have been used from the baseline findings. With 12 questions on 5-point scale from strongly disagree to strongly agree. A student who responded “strongly agree” to all 12 questions would have a score of 100%, and a student who responded “agree” to all 12 questions would receive a score of 75%; neither agree or disagree 50 %. In addition, agency focuses on the students’ voice in making choices about school enrolment. At Baseline, this indicator was determined on an average of the five-point scale in how strongly beneficiaries agree that they have a voice in decisions about their own enrolment.
|  |  | 73.6% | Actual | Actual
|  | Children with Disabilities (disaggregate by gender, disability, JSS/PS, district, age) | 75.6% | Actual | Actual
| IO 3.2: % of marginalised girls and children with disabilities in the GEC cohort reporting feeling safe, secure and included in the learning environment | Girls (disaggregate by JSS/PS, district, age) |  | Maintain | Maintain |  | GEC cohort' - PS and JSS girls and children with disabilities that were a part of the GEC 1 project (2013-2016) At Baseline, 'Safe and secure' - not mistreated i.e. not beaten/flogged, shouted at, stigmatized. At subsequent evaluation points a more positive measure of safety and security should be explored. 'Included' - involved by teaching staff, involved in discussions and asking questions, CWDs felt supported post adaptation
|  |  | 91.8% | Actual | Actual
|  | Children with Disabilities (disaggregate by gender, disability, JSS/PS, district, age) | 90.48% | +1% | +1%
| 1O 3.3: % of marginalised children with disabilities in the GEC cohort reporting school facilities are accessible post-school adaptation (model schools) | Children with Disabilities (disaggregate by gender, disability, JSS/PS, district, age) | 0 (activities were not running at baseline) | Actual | Actual
| IO 3.4: % (and type) of follow-up actions carried out by school management (HTs and BoGs) in targeted JSS schools (based on feedback raised by children through feedback boxes - scorecarding) | Follow up actions (disaggregate actions taken number and type at school, chiefdom and district level) | 0 (activities were not running at baseline) |  | Target | Functional BOGs in targeted JSS schools and BOGs are engaged with the school governance processes. | Follow-up actions: Processes done by School management (HTs, BoGs, CTAs, ) to mitigate or respond to concerns raised by children through the feedback boxes including referrals made to relevant child protection actors in the community (CWC, Police, UNICEF Safety Committees, NGOs, CBOs etc.) for example changes recommended by girls and boys like structural adaptations to accommodate needs of children with disabilities 'Targeted JSS schools' - the 180 schools where scorecarding is implemented during the lifetime of projects School governance/management: Head Teachers/ Board of governors & CTAs
|  |  |  | Actual | Actual
|  |  |  | +6% | +6%
|  |  |  | +6% | +6%
|  |  |  | +6% | +6%
| IO 3.5: # of Community Based Roving/ Rehabilitation Volunteers (CBRVs) demonstrating increased knowledge on Inclusive Education to support children with disabilities and their families in the project | CBRVs (disaggregate by gender, district and disability) | 0 (activities were not running at baseline) | Actual | Actual | CBRVs are engaged with the project. | Knowledge - The ability of CBRVs to raise awareness on disabilities in communities. Their ability to promote the importance of inclusive education through disseminating inclusive messages (e.g. allow all children, including children with disabilities, girls and boys to go to school) Inclusive Education - Training in disability, inclusion, advocacy, identification and screening, data collection, child protection, mapping and referral of services for persons with disability...
RISK RATING High | External Evaluators: Baseline, Midline and Endline: Household survey with parents and children, Girls School survey and Qual interviews: FGDs and KIIs with children, parents, teachers (PVs), LAs and STs. Project Monitoring data: EE's Review of data from study groups observations, KIIs and FGDs with children, PVs and head teachers/members of SMCs, records of follow up on issues raised by children (scorecarding). Classroom observations. Review of agenda, minutes and attendance, and records of observations from SMC/BOG meetings. scorecarding monitoring summary sheet, Records of action plans feedback processes followed (School management records ), CP referral records and processes followed by schools (school management records). KIIs with beneficiaries. Review of agenda, minutes and attendance from HTs, BoGs , CTAs meetings. CPD review tool. Child protection referral mapping form. HI inclusive education tools.
INTERMEDIATE OUTCOME 4 | IO 4 Indicators |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020 | Assumptions | Definitions/Index of questions
Improved economic empowerment at the household level to cover educational costs | IO 4.1: % of the GEC cohort (of targeted households) reporting confidence and skills in financial planning and management | Girls (disaggregate by JSS/PS, district, age) |  | +7% | +10% | Beneficiary households are willing and economically able to participate in the VSLA programme | Note that at baseline the project had not yet rolled out the VSLA component. % of HH reporting being engaged in one or more savings activities and how this is allocated to their children’s education, and perceptions of financial literacy, planning and management (via KIIs/FGDs), 'GEC cohort '- girls and children with disability that were a part of the GEC 1 project (2013-2016) 'Targeted households - the households selected based on pre-defined criteria of degree of marginalisation and need.
|  |  | 36.83% | Actual | Actual
|  | Children with Disabilities (disaggregate by gender, disability, JSS/PS, district, age) | 33.7% | Actual | Actual
| IO 4.2: % of parents/caregivers in targeted households who contribute to their child's educational costs (those not already covered by Free Quality School Education) | Girls (disaggregate by JSS/PS, district, age, type of costs covered) |  | +4% | +4% |  | Educational costs'- Paying school fees, purchasing uniforms, text books etc. 'GEC cohort '- girls and children with disability that were a part of the GEC 1 project (2013-2016) 'Targeted households - the households selected based on pre-defined criteria of degree of marginalisation and need
|  |  | 68.72% | Actual | Actual
|  | Children with Disabilities (disaggregate by gender, disability, JSS/PS, district, age, type of costs covered) | 66.67% | Actual | Actual
RISK RATING High | External evaluators: Baseline, Midline and Endline: Household survey with parents and children and qual interviews: FGDs and KIIs with parents and children, VSLA groups. KII and FGD Interviews with HTs, and SMC/BOGs. Project monitoring: EE's Review of on-going monitoring data on VSLAs (VSLA household questionnaire and observations, records review tool). FGDs and KIIs with targeted beneficiary households and VSLA groups. Pre/post economic assessment (based on reverification data).
INTERMEDIATE OUTCOME 5 | IO 5 Indicators |  | Baseline - March 2018 | Midline - December 2019 | Endline - December 2020 | Assumptions | Definitions/Index of questions
Improved attitudes and perceptions of communities and government officials around girls access and inclusive education | IO 5.1: % of communities (including parents/caregivers, SMCs and BOGs) who report positive perceptions around girls and children with disabilities accessing education. | Parents/caregivers (disaggregate by attitudes towards girls/cwd, gender, district, JSS/PS) |  | 0 (Maintain) | 0 (Maintain) | Communities are supportive of interventions and continue to be involved. Bursaries incentivise girls to enrol and stay in school and attend regularly. Schools are willing to enrol children with disabilities. | At baseline, improvement based on % of treatment households who agree or strongly agree that subgroup has a right to go to school. At subsequent evaluation points a more nuanced exploration of people's attitudes to girls' rights to education should be undertaken. The evaluations may want to explore further the link between changes in attitudes and behaviours.
|  |  | 98.48% (for girls) and 90.15% (for CWDs) | Actual | Actual
|  | Other community members (disaggregate by gender, district) | 0 (activities were not running at baseline) | Actual | Actual
|  | SMC members (disaggregate by gender, district) | 0 (activities were not running at baseline) | Actual | Actual
|  | BOG members (disaggregate by gender, district) | 0 (activities were not running at baseline) | Actual | Actual
| IO 5.2.: # of government officials (MOBSSE, MSWGCA) at district level who are aware of inclusive education teaching practices and report positive attitudes towards it. | MOBSSE officials (disaggregate by gender, district) | 0 (activities were not running at baseline) |  | Target | Political will of government to work in partnership with INGOs is maintained. The Ministry of Education and other ministries continue to support the project. | Improvement will be based on their knowledge around inclusive education being implemented in SLE schools (from the model presented by GATE GEC) and the demonstration of the ability/skills of MOBSSE and MSWGCA in undertaking joint activities and initiatives related with inclusive education e.g. i.e. teacher training, accessibility and adaptation works.
|  |  |  | Actual | Actual
|  | MSWGCA officials (disaggregate by gender, district) | 0 (activities were not running at baseline) |  | Target
|  |  |  | Actual | Actual
RISK RATING High | External evaluators: Baseline, Midline and Endline: Household survey with parents and children and qual interviews: FGDs and KIIs with parents and children. KII and FGD Interviews with MOBSSE and MSWGCA officials. Project monitoring: EE's Review of on-going monitoring data on stakeholder engagement tool, FGDs and KIIs with MOBSSE and MSWGCA officials. Pre/post training assessments (from trainings involving MOBSSE and MSWGCA), pre and post from PV training.

## Outcome 3
|  | Contributing Intermediate outcomes | Intermediate outcome indicators
OUTCOME 3 - Sustainability | Community | Improved attitudes and perceptions of households and communities to invest in children's education and include them in decision-making |  | Baseline - March 2018 Scale (1-4) | Midline - December 2019 Scale (1-4) | Endline - December 2020 Scale (1-4) | Assumptions | Definitions
Project demonstrates that the changes it has brought about which increase learning and transition through education cycles are sustainable: Performance against comprehensive sustainability scorecard (scores 1-4). |  |  | Indicator 1 - Parents, caregivers and community members allocating financial resource, to progress girls’ and children with disabilities’ educational rights |  |  | Target | Beneficiaries and communities (including boys) are supportive of interventions and continue to be involved. Schools and their communities are receptive to field staff collecting data from both schools as well as study groups. | Actively engaged: Children discussing school and education with parents, actively open and making decisions related to their education, vocalising learnings and school activities etc.
[5 empty] | Actual | Actual
|  |  | Indicator 2 - GATE GEC parents, caregivers reporting beneficiaries are actively involved in making decisions around their education. |  |  | Target
[5 empty] | Actual | Actual
|  |  | Overall Score (1-4) |  | 3 - Becoming established | 4 - Established
|  |  |  | 2: Emerging | Actual | Actual
| Impact weighting (%) | 40% |  | External evaluators: FGDs (annual with baseline, midline and endline), KIIs, Household survey. Project monitoring: EE's review of observations of VSLA groups, FGDs with groups, evidence of them using savings to support educational activities or other life choices of children. Scorecarding monitoring and review of school development/action plans developed by school governance bodies.
| School | Improved quality of teaching, improved school management and governance and increased commitment to practices which encourage beneficiaries' self esteem and safety |  | Baseline - March 2018 Scale (1-4) | Midline - December 2019 Scale (1-4) | Endline - December 2020 Scale (1-4)
|  |  | Indicator 1- % of school staff (HTs, teachers) in GATE GEC schools planning to continue providing study group sessions, scorecarding activities, trainings to teachers, CPD of teachers after the end of the project |  |  | Target | Schools and their communities are receptive to field staff collecting data from both schools as well as study groups. Schools (all types of school staff), LAs/STs are engaged and value programme. Schools continue to be involved. | Functional SMCs and BOGs - Meeting once per term, development of actions plans, follow up on the school improvement plans (help in school management, school problems like absenteeism (for both teachers & students), drop outs, child safeguarding issues) An end result of SMCs, BOGs activities would be "functional SMCs, BOGs" STs - are young women involved in GEC 1 and continue to be supported through the form of learning materials provided on tablet devices.
[5 empty] | Actual | Actual
|  |  | Indicator 2 - Teachers, headteachers and other school staff have the skills, knowledge and materials on inclusive education with non-GATE GATE schools (CPD, trainings, manual) |  | Actual | Actual
|  |  | Indicator 3 - Number of STs (cohort 1,2) enrolled in the government payroll and appointed to schools in rural areas across SLE |  |  | Target
[5 empty] | Actual | Actual
|  |  | Indicator 4 - % of functional SMCs, BOGs in GATE GEC schools |  |  | Target
[5 empty] | Actual | Actual
Indicator 5 - % of GATE GEC beneficiaries who feel that their school is a safe place for them (this still is being explored further within the project and will be finalised before the midline commences)
|  |  | Overall Score (1-4) |  | 3 - Becoming established | 4 - Established
|  |  |  | 2: Emerging | Actual | Actual
| Impact weighting (%) | 40 |  | External evaluators: FGDs and KIIs with school staff (including LAs/STs) (baseline, midline, endline). School observations. Project monitoring: EE's review of FGDs, and KIIs with SMC members, head teachers, girls and children with disabilities in schools, classroom observations in schools, score-carding monitoring and action plan phase.
| System | Improved quality of teaching through better school governance; strengthened understanding and commitment to support inclusive education from government officials |  | Baseline - March 2018 Scale (1-4) | Midline - December 2019 Scale (1-4) | Endline - December 2020 Scale (1-4)
|  |  | Indicator 1: Level of engagement with district and national government stakeholders (MOBSSE and MSWGCA) to support education provision to girls and children with disabilities education nationally (specifically on the Free Quality Education Programme) |  |  | Target | Political will of government to work in partnership with INGOs is maintained. BOG. SMC and CTAs are functioning in communities BOG. SMC and CTAs are willing to engage with project Schools and their communities are receptive to field staff collecting data from both schools as well as study groups. | Increased engagement' includes attendance and participation in working groups, steering committee meetings, joint monitoring visits, other events/meetings that are hosted by the consortium involving government officials. 'Education plans' - plans developed based on increased engagement activities above. 'Holding schools accountable': SMCs and BoGs are monitoring the work of the head teachers for example through follow up meetings, monitoring visits to the school, interactions with teachers-students and parents.
[5 empty] | Actual | Actual
|  |  | Indicator 2 - District and national government stakeholders (MOBSSE and MSWGCA) developing education plans based on project activities (Inclusive Education, training to PVs, LA/ST component) to continue in existing GATE GEC schools, and cascade successful models to non GATE GEC schools |  |  | Target
[5 empty] | Actual | Actual
|  |  | Indicator 3 - SMCs, BOGs demonstrating holding school staff (headteachers) accountable for decision made on school governance and management decisions (from the action and school development plans) |  |  | Target
[5 empty] | Actual | Actual
|  |  | Overall Score (1-4) |  | 2: Emerging | 3 - Becoming established
|  |  |  | 1: Latent – but not in all areas | Actual | Actual
RISK RATING High | Impact weighting (%) | 20 |  | External evaluators: KIIs and FGDs with SMC, BOGs, local and national government staff (including MEST, DFID). Project monitoring: EE's review of notes/minutes from steering committees involving local and national stakeholders, review of stakeholder engagement tool. Review of notes/actions developed from Joint monitoring visits with MEST officials, Scorecarding monitoring and review of school development/action plans developed by school governance bodies. Pre and post training assessments (SMC/BOG training) and review of action plans developed. KIIs and FGDs with SMC and BOG members, HTs and local/national government officials.

## Outputs
OUTPUT 1 | Output Indicator 1.1 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 - | Assumptions | Definitions/rationale
Marginalised girls and children with disabilities, and their parents/caregivers are provided support for beneficiaries, to attend and learn through PSS, to JSS and JSS to post JSS. | % of the GEC cohort receiving bursaries (disaggregate the data by gender, disability and type (severity), age (grade) and geographical location.) | Girls and CwD (disaggregate by gender, type of disability, district, JSS/PS, intervention type) | n/a | Target 90% beneficiaries receive and use a complete bursary set (in the areas of HI/AA) | n/a (no longer providing bursaries due to FQSE, see rationale) | n/a | GEC cohort and communities continue to engage in the GEC Project. Bursaries incentivise cohort to enrol and stay in school and attend regularly. The Ministry of Education continues to support the project. | GEC cohort '- girls and children with disability that were a part of the GEC 1 project (2013-2016) The government introduced it's Free Quality School Education mandate in 2018 - agreeing to pay all school fees and provide bursary items to students. As a result, the GEC project is no longer allowed to distribute bursaries beyond Yr2 and only in areas where these items had already been procured (HI and AA districts). We will provide the following bursary items for Yr2 in HI/AA districts as follows: JSS:- 6 exercise books. 6 pens per year. 1 geometry sets. 1 school bag. PSS:- 6 pencils,2 erasers, 2 sharpeners, 6 exercise books, 1 school bag All the beneficiaries will also receive two uniforms for the academic year. Targeted schools are also provided with core textbooks.
|  |  | n/a | Actual | Actual | Actual
|  |  | n/a | Actual | Actual | Actual
Source
Bursary distribution tool (use of bursary distribution tool to accurately capture bursaries are going to the correct beneficiaries) - disaggregated by gender and disability, annual beneficiaries reverification tool. Bursary usage monitoring form (within the school term of the bursaries' distribution baseline vs endline on bursary usage and impact to attend).
| Output Indicator 1.2 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 - | Assumptions | Definitions/rationale
| Average attendance rates (%) of GATE GEC cohort in study groups | Girls and CwD (disaggregate by gender, type of disability, district, JSS/PS, intervention type) | n/a | 80% | 85% | 90% | Beneficiary households are willing and economically able to participate in the VSLA programme. The Ministry of Education and the Ministry of Social Welfare continue to support the project. Beneficiaries likely to attend when there's someone to walk home with and sufficient food so they do not go hungry. | Study group sessions - after school sessions that take place for 1 hour two times a week. Attending - the number actually in attendance on that day of monitoring compared to the number of GEC cohort expected to attend. Improving attendance monitoring and follow-up systems is a key focus of the project, and should strengthen year on year as the project works closely with schools to implement changes in attitudes and protocols in this area.
|  |  | n/a | Actual | Actual | Actual
|  |  | n/a | Actual | Actual | Actual
Source
Study group observation tool (numbers attending), study group monitoring (parents, beneficiaries, parents)
| Output Indicator 1.3 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 - | Assumptions | Definitions/rationale
| % of GEC cohort households actively engaged in the programme's VSLAs (disaggregated by gender, age, geographical location of beneficiaries) | Households(disaggregate by how many are GATE-GEC, gender of beneficiaries, disability, JSS/PS, district) | n/a | tbc - expected Jan 2019 | TBC | TBC | Beneficiary households are willing and economically able to participate in the VSLA programme. The Ministry of Education and the Ministry of Social Welfare continue to support the project. | Households - the households selected based on pre-defined criteria of degree of marginalisation and need Actively engaged - targeted households who are active members of VSLA groups and regularly make savings in the VSLA groups VSLAs are composed of 25 members mixed GATE-GEC and non-beneficiary households. GATE-GEC households will be given priority to join each group.
|  |  | Actual | Actual | Actual | Actual
|  |  | Actual | Actual | Actual | Actual
Source
Baseline, midline, endline and GATE GEC VSLA target household survey, GATE GEC VSLA observation and records review tool, Pre and post training assessments.
| Output Indicator 1.4 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 - | Assumptions | Definitions/rationale
| % of School Management Committees (SMCs) in Primary Schools that have developed an annual school development plan (including types of activities planned). | SMCs (disaggregate numbers in groups by gender, district) | n/a | n/a | 50% | 60% | SMCs' members are willing to participate in the programme. The Ministry of Education continues to support the project. | SMCs - 250 Primary schools were reverified during the last re-verification process. SMCs are composed of (a) The head – teacher of the school, (b) The Inspector of Schools or his/her representative (now Deputy Director without voting right), (c) The traditional ruler of the village or area concerned, (d)Chairman of the Community Teachers Association or his/her deputy, (e)The proprietor’s representative, (f) A female member or female representative of the Chiefdom Education Committee, (g) A prominent educationist. The Education Act of 2004 provides for a membership of 7 as listed above and that participation in the SMC is voluntary and does not include financial reward. Annual development plan - The SMCs are supposed to develop annually a plan to improve the school under the following areas: school structure, school environment, teachers management, learning material.
|  |  | n/a | n/a | Actual | Actual
Source
School management monitoring tool for SMCs (to be developed). KIIs and FGDs with SMC members
| Output Indicator 1.5 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 - | Assumptions | Definitions/rationale
| % of targeted Board of Governors (BoGs) in Junior Secondary schools that have developed a school action plan (including types of actions developed) | BOGs (disaggregate numbers in groups by gender, district) | n/a | n/a | 50% | 60% | BoGs' members are willing to participate in the programme. The Ministry of Education continues to support the project. | Targeted BoGs - the BoGs of the 186 JSS targeted by the project School Action plan - the main responsibility of the BoGs is to supervise the Head Teachers and to support then in line managing the teachers. Therefore every BoGs should develop annually a plan to support the Head Teachers in the management of the school staff and in addressing HR issues.
|  |  | n/a | n/a | Actual | Actual
Source
School management monitoring tool for BoG (to be developed) . KIIs and FGDs with BOG members
| Output Indicator 1.6 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| # of GATE GEC Children with disabilities (CWDs) receiving assistive devices and individualised treatments (disaggregated by gender, age and type of disability) | CWDs (by gender, JSS/PS, district, disability) | n/a | 200 (cumulative) | 500 (cumulative) | 600 (cumulative) | Children with disabilities in GEC cohort continue to engage in the GEC Project. The Ministry of Education continues to support the project. | Assistive devices - Devices and equipment that assist people with disability to lead a more independent life and take an active part in the community are called assistive devices. Individualised treatments - Prescribed medicines and medical practices administered to children with disabilities based on their individual impairment needs. CBRVs together with IEDOs (trained in disability, inclusion and identification and screening) pre-identified and screened children in GATE GEC schools for the provision of the first round of assistive devices. ALL children with disability registered under GATE GEC project will be screened during the re-verification exercise to be conducted in October-November 2018
|  |  | n/a | Actual | Actual | Actual
|  |  | n/a | Actual | Actual | Actual
Source
Medical assessment tools (follow up section; beneficiaries re-verification tool Individual follow up, usage of the device monitoring tool.
| Output Indicator 1.7 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| # of Community Based Rehabilitation Volunteers (CBRVs) actively engaged in the programme in supporting children with disabilities and their families in the project into education | CBRVs (disaggregate by gender, disability, district) | n/a | 136 | 136 | 136 | CBRVs are willing to participate in the programme. HI is able to replace volunteers where there is natural attrition. The Ministry of Education continues to support the project. | Actively engaged and Supporting: includes training in disability, inclusion, advocacy, identification and screening, data collection, child protection, mapping and referral of services for persons with disability.
|  |  | n/a | Actual | Actual | Actual
|  |  | n/a | Actual | Actual | Actual
Source
Pre-Post training assessment tool.; Event completion forms. Pedagogical practices tool and inclusive school environment and academic result
IMPACT WEIGHTING (%) 35% | Input (HR) |  | DFID (FTEs) | Consortium (FTEs) | Others (FTEs)
RISK RATING High | Inputs (£) |  | DFID (£) 6,822,267 | Consortium (£) 43,531 | Others (£) | DFID share (%) 99%
OUTPUT 2 | Output indicator 2.1 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
Increased number of skilled PVs, LAs/STs (who support the cohort beneficiaries) to improve learning of marginalised girls and children with disabilities | # of Programme Volunteers (PVs) and cohort 3 Learning Assistants (year 1) /Students Teachers (year 2 and 3) engaged in the GATE GEC project | PVs and cohort 3 LAs/STs (disaggregate by gender, district) | n/a | 1774 of PVs and LAs/STs engaged in the GATE GEC project (=1524 PVs and 250 cohort 3) | 1774 of PVs and STs engaged in the GATE GEC project | 1774 of PVs and STs engaged in the GATE GEC project | PVs are supportive of girls and children with disabilities being in education. LAs/STs continue to engage with the project. Tutorial support adequately prepares LAs for their examinations through quality training and support. The project is able to replace PVs where there is attrition, and some expansion to new schools is needed as beneficiaries move schools. The Ministry of Education continues to support the project. | Engaged- Those who were recruited as PVs and LAs, who attended the trainings and are: - running study group sessions (PVs); - attending tutorial classes and undergoing school practice experience. 'Skilled:' provided support through teaching/learning materials , training and adapted learning infrastructure
|  |  | n/a | Actual | Actual | Actual
|  |  | Actual | Actual | Actual | Actual
Source
School survey with HT, MOU developed with schools. KIIs with HTs. Study group monitoring of PVs, beneficiaries, self assessment forms completed by LAs and STs
| Output indicator 2.2 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| % of Learning Assistants (LAs) passing the marked assignment | LAs (disaggregate by district) | n/a | 230 (out of 250) of LAs passing the marked assignment | n/a | n/a | LAs continue to engage with the project. LAs are female offering female role models within the classroom. They will become STs in Yr 3/4. Tutorial support adequately prepares LAs for their examinations through quality training and support. The Ministry of Education continues to support the project. | Passing - LAs scoring 20% in each Maths Marked assignments and 30% in each English Marked Assignments. Marked assignment - These are tests administered to LAs while preparing for the Teacher Training College entrance exams. The Marked Assignments enable us determine the LAs' preparedness for the college entrance exams, areas they require support and how to provide that support. These are administered after completing each subject unit (Maths and English).
|  |  | n/a | Actual | Actual | Actual
Source
LA marked assignment results.
| Output indicator 2.3 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| % of Student teachers completing teacher training college course (cohort 1 and 2 (GEC 1) and cohort 3 (GATE GEC) | STs (disaggregate by cohort, district) | n/a | TBC - clarification needed from OU/FAWE (expected January 2019) | TBC | TBC | STs continue to engage with the project. The Ministry of Education continues to support the project and teachers. | Teacher Training College exams (require further clarity from OU/FAWE)
|  |  | n/a | Actual | Actual | Actual
Source
ST tracking data/monitoring log (measurement process to be confirmed with FAWE and OU)
| Output Indicator 2.4 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| % of GEC beneficiaries reporting positive perceptions of PVs teaching skills and support in the classroom | Girls and CwD (disaggregate by gender, type of disability, district, and by JSS/PS) | n/a | TBC - we will have a better sense from Study Group monitoring data (set in first quarter of 2019) | TBC | TBC | PVs are supportive of girls and children with disabilities being in education. The Ministry of Education continues to support the project. | Improved perceptions include beneficiaries reporting PVs are teaching in an effective, supportive and inclusive manner. Observations also show that the teachers are using the methods taught in training in the classroom, and the how children react.
|  |  | n/a | Actual | Actual | Actual
Source
Study group monitoring form beneficiaries, parents/caregivers, PVs, CPD review tool. Study group observation tool.
| Output Indicator 2.5 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| % of PVs recorded to have attended teacher learning circle in a quarterly basis | PVs (disaggregate by gender, JSS/PS, district) | n/a | 25% | 50% | 100% | Headteachers are supportive of the enhanced CPD component PVs continue to be engaged in the project | Teacher learning circle are defined in Conducting Teacher Learning circle tool and are discussions with groups of PVs at school or school cluster level facilitated by field staff or headteacher, including demonstration and discussion of participatory activity/pedagogical approaches.
|  |  | n/a | Actual | Actual | Actual
Source
PV coaching tool, CPD review tool.
| Output Indicator 2.6 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| % of PVs recorded to have attended at least one coaching observation session in a quarterly basis (disaggregated by gender) | PVs (disaggregate by gender, JSS/PS, district) | n/a | 25% | 50% | 100% | Headteachers are supportive of the enhanced CPD component PVs continue to be engaged in the project | Coaching/observation session is the observation of a PV practice in a study group session by field staff or headteacher utilising the coaching/observation tool and with subsequent feedback/coaching to the PV.
Source
PV coaching observation tool, CPD Reporting tool
| Output Indicator 2.7 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| % of PVs reporting positive use of at least 3 (three) key teaching skills during coaching/observation sessions | PVs (disaggregate by gender, JSS/PS, district) | n/a | 50% | 75% | 100% | PVs are supportive and engaged with the coaching/observation session PVs continue to be engaged in the project | Coaching/observation session is the observation of a PV practice in a study group session by field staff or headteacher utilising the coaching/observation tool and with subsequent feedback/coaching to the PV. ‘Positive’ are those marked with happy faces in the coaching/observation tool. ‘Key teaching skills’ include literacy/numeracy learning objective, inclusive/children-centred strategies, classroom management, atmosphere and checking for understanding.
Source
PV coaching observation tool, CPD review tool, Study group observation tool
IMPACT WEIGHTING (%) 35% | Input (HR) |  | DFID (FTEs) | Consortium (FTEs) | Others (FTEs)
RISK RATING Medium | Inputs (£) |  | DFID (£) 1,690,998 | Consortium (£) 245,004 | Others (£) | DFID share (%) 89%
OUTPUT 3 | Output Indicator 3.1 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
Marginalised girls and children with disabilities are supported to learn in a safe and inclusive learning environment | % of targeted JSS school stakeholders involved in the scorecarding process at the beginning of the school year | Disaggregated by children, parents/caregivers, BoG members, HTs and teachers, district | n/a | 80% | 80% | 80% | Girls , children with disabilities, , parents and school-community stakeholders continue to engage with education and in the learning environment. The Ministry of Education continues to support the project. | Involved - meaning the school stakeholders attending the scorecarding training, taking part in scoring the performance of the school on safety and inclusiveness and developing action plans to improve the scoring. Scorecarding process - it is a methodology for recording scores to measure achievement of progress towards a particular goal on improving the school environment concerning safety and inclusiveness 'Targeted JSS schools ' - the 180 schools where scorecarding is implemented during the lifetime of projects
|  |  | n/a | Actual | Actual | Actual
|  |  | n/a | Actual | Actual | Actual
Source
Scorecarding attendance registers (disaggregated by gender, roles, disability and location). Study groups monitoring form for beneficiaries, PVs, parents. KIIs and FGDs with children, parents, BOGs, teachers.
| Output Indicator 3.2 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| # of score carding action plans developed by targeted JSS school stakeholders on an annual basis | Disaggregated by schools and districts | n/a | 60 | 120 | 180 | BoGs' , CTAs, & HTs members are willing to participate in the programme . 'The Ministry of Education continues to support the project. | ‘Scorecarding action plans' -planned actions to promote a safe and inclusive school environment in target schools. These plans are developed after the GEC scorecarding activity and a follow-up session is held one year later to help determine progress. 'Targeted JSS schools ' - the 180 schools where scorecarding is implemented during the lifetime of projects
|  |  | n/a | Actual | Actual | Actual
Source
KIIs with beneficiaries. Review of agenda, minutes and attendance from BoGs SMC meetings. Quarterly scorecarding summary sheet, Scorecarding-roll-out activity reports ( record of school action plans and processes followed) KIIs with head teachers , KIIs with members of school management (HTs BoGs & CTAs ), KII with beneficiaries and children in scorecarding target schools.
| Output Indicator 3.3 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| # and type of feedback received from girls and boys through feedback boxes in the targeted JSS schools on a quarterly basis. | Disaggregated by schools, districts and type of feedback | n/a | tbc - expect January 2019 in discussion with Safeguarding Specialist | tbc | tbc | School- stakeholders (HTs, BoGs, CTAs, PVs) continue to engage with children and embrace feedback to improve learning environment. feedback boxes remain in place and functional. Feedback rates go up each year as girls/ children with disabilities feel empowered to report issues through the feedback boxes. The Ministry of Education continues to support the project. | ‘Feedback’ includes any ideas/ questions and concerns that children bring to attention of school management through the feedback boxes in target JSS schools concerning children safety and inclusiveness in the school. 'Feedback boxes’ are wooden boxes placed in school premises to act as feedback and reporting points by children in target JSS schools. 'Targeted JSS schools ' are the 180 schools where scorecarding is implemented during the lifetime of project.
|  |  | Actual | Actual | Actual | Actual
|  | Disaggregate by girls and CwDs (if this is known) | Actual | Actual | Actual | Actual
Source
Quarterly scorecarding summary sheet, Records of action plans and processes followed (monitoring log), referral records and processes followed, KII with beneficiaries and children in scorecarding target schools.
| Output Indicator 3.4 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| # of schools that are adapted to be disability friendly (model schools). | PS schools (disaggregated by district) | n/a | 3 | 9 | 18 | School, community and district stakeholders will be committed and will continue to engage with the project. The Ministry of Education continues to support the project. | "disability friendly" - Schools that have been specifically adapted to the needs of children with disabilities e.g. ramps, well designed classrooms etc, that provides a conducive learning environment (with a variety of cognitive and social experiences).The school assessment will identify what are the needs of children at that school.
|  |  | Actual | Actual | Actual | Actual
|  |  | Actual | Actual | Actual | Actual
Source
Pedagogical practice and school environment monitoring tools. Quarterly and annual project reporting.
IMPACT WEIGHTING (%) 25% | Input (HR) |  | DFID (FTEs) | Consortium (FTEs) | Others (FTEs)
RISK RATING Medium | Inputs (£) |  | DFID (£) 739,752 | Consortium (£) 54,415 | Others (£) | DFID share (%) 95%
OUTPUT 4 | Output Indicator 4.1 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
Programme evidence and learning is shared with key educational decision makers and actors to influence the Sierra Leonean Education sector | # of MOBSSE and MSWGCA officials participating in trainings on inclusive education and gender sensitive pedagogical teaching practices. | Disaggregate by MOBSSE and MSWGCA members (male and female, district) | 20 | 35 (discrete) | 35 (discrete) | 35 (discrete) | Political will of government to work in partnership with INGOs is maintained. The Ministry of Education continues to support the project. | The ability/skills of MOBSSE and MSWGCA in undertaking joint activities and initiatives related with inclusive education (training in disability, inclusion, advocacy, identification and screening, data collection, child protection, mapping and referral of services for persons with disability, teacher training, accessibility and adaptation works)
|  |  | Actual | Actual | Actual | Actual
Source
Stakeholder Engagement tool. Minutes from working groups, executive meetings. KIIs and FGDs with MEST officials
| Output Indicator 4.2 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| # of education-related events consortium partners share evidence and learning from the GATE GEC project with key educational stakeholders. (each district will organise a learning event + one national level event per year) | # of events, district, type/gender of stakeholder | n/a | n/a | 6 | 12 (cumulative) | Political will of government to work in partnership with INGOs is maintained. The Ministry of Education continues to support the project. | Events include steering committees, working groups, workshops and other meetings that involved government officials and key education stakeholders.
|  |  | n/a | n/a | Actual | Actual
Source
Stakeholder Engagement tool. Minutes and related documents including presentations from events, KIIs and FGDs with key educational stakeholders.
| Output Indicator 4.3 |  | Year 1 - Year End March 2018 | Year 2 - Year End March 2019 | Year 3 - Year End March 2020 | Year 4 - Year End 2021 | Assumptions | Definitions/rationale
| # of MOBSSE and MSWGCA officials supporting joint monitoring visits | Disaggregate by MOBSSE and MSWGCA members (male and female, district) | n/a | n/a | 12 (discrete) | 12 (discrete) | Political will of government to work in partnership with INGOs is maintained. | Joint monitoring visits include key government officials at district and national level to monitor GATE GEC school activity Visits are expected twice a year at national and district level.
|  |  | n/a | Actual | Actual | Actual
Joint monitoring visit notes and action plans. Stakeholder Engagement tool. KIIs and FGDs with key educational stakeholders. Source
Attendance sheets (with roles and orgs), agenda and minutes from key events, activity report Pre and post training assessment -
IMPACT WEIGHTING (%) 5% | Input (HR) |  | DFID (FTEs) | Consortium (FTEs) | Others (FTEs)
RISK RATING High | Inputs (£) |  | DFID (£) 116,920 | Consortium (£) | Others (£) | DFID share (%) 100%
Note on I37: McMillan, Caitilin: how will we review/capture active engagement